## Main sheet
Week | Sprint | Release # | Tasks | Difficulty | Point (estimate of point) | Status
2023-01-06 | Sprint 1 |  | Create Project Planning Documents | Medium | 5 | Complete
2023-08-06 | Sprint 2 |  | Trello Setup | Easy | 2 | Complete
|  | 1.00 | Git + Github Setup | Easy | 2 | Complete
6/15/2023 | Sprint 3 |  | Create Project | Medium | 5 | Complete
|  |  | Create Project scaffolding | Easy | 2 | Complete
6/22/2023 | Sprint 4 |  | Run App on local | Medium | 5 | Complete
|  | 1.10 | Run App on Azure Bash | Easy | 2 | Complete
6/29/2023 | Sprint 5 |  | Config Github Actions | Medium | 5 | Complete
|  |  | Test Github Actions | Easy | 2 | Complete
2023-05-07 | Sprint 6 |  | Create Terraform file to create Azure App Service | Medium | 5 | Complete
|  | 1.20 | Run Terraform to create Azure App Service | Easy | 2 | Complete
2023-12-07 | Sprint 7 |  | Config Azure Devops Organization and Project | Easy | 2 | Complete
|  |  | Connect Azure Devops with Github | Easy | 2 | Complete
7/19/2023 | Sprint 8 |  | Create Azure Pipeline | Hard | 8 | Complete
|  | 1.30 | Test Run Azure Pipeline | Medium | 5 | Complete
7/26/2023 | Sprint 9 |  | Config locust test | Medium | 5 | Complete
|  |  | Run locust test | Easy | 2 | Complete
2023-03-08 | Sprint 10 |  | Update Readme file | Easy | 2 | Complete
|  |  | Take Screenshots | Easy | 2 | Complete
|  |  | Record a demo video | Medium | 5 | Complete
2023-10-08 | Sprint 11 | 1.40 | QA | Medium | 5 | Complete
|  |  | Goals | Goals
Q2 |  |  | Complete Create and Run Project on Local
Q3 |  |  | Complete Project CI/CD on Azure Services
QA
Yearly Plan |  |  | Enhance, Maintenance and Expansion of new Modules